## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | October – Week 1 | Tester | Product not saved when fields are empty | Sprint 1 | Backend Dev | Functional | Added validation | Closed | Fixed
2 | October – Week 1 | Tester | Stock quantity not updating properly | Sprint 1 | Backend Dev | Logical | Fixed update logic | Closed | Verified
3 | October – Week 2 | Tester | Inventory list loads slowly | Sprint 1 | Backend Dev | Performance | Optimized query | Closed | Improved
4 | October – Week 2 | Tester | Delete option visible without admin login | Sprint 2 | Backend Dev | Security | Added role check | Closed | Secured | Access restricted
5 | October – Week 3 | Tester | Low stock alert not triggered | Sprint 2 | Backend Dev | Functional | Corrected condition | Closed | Working
6 | October – Week 3 | Tester | Duplicate products allowed | Sprint 2 | Backend Dev | Functional | Added uniqueness check | Closed | Fixed
7 | October – Week 4 | Tester | Search returns wrong results | Sprint 2 | Backend Dev | Logical | Fixed filter logic | Closed | Correct
8 | October – Week 4 | Tester | UI misalignment in inventory page | Sprint 2 | Frontend Dev | UI | Updated CSS | Closed | Resolved
9 | October – Week 5 | Tester | Pagination not working | Sprint 3 | Frontend Dev | Functional | Fixed pagination logic | Closed | Verified
10 | October – Week 5 | Tester | Error message unclear on failure | Sprint 3 | Frontend Dev | Usability | Improved messages | Closed | Improved
11 | November – Week 1 | Tester | Session not expiring after logout | Sprint 3 | Backend Dev | Security | Fixed session handling | Closed | Secure
12 | November – Week 1 | Tester | Dashboard data mismatch | Sprint 3 | Backend Dev | Data | Corrected query | Closed | Accurate
13 | November – Week 2 | Tester | Product delete confirmation missing | Sprint 3 | Frontend Dev | UI | Added confirmation popup | Closed | Added
14 | November – Week 2 | Tester | Supplier data not saved | Sprint 4 | Backend Dev | Functional | Fixed save API | Closed | Fixed
15 | November – Week 3 | Tester | Report export fails sometimes | Sprint 4 | Backend Dev | Functional | Fixed export logic | Closed | Stable
16 | November – Week 3 | Tester | Print layout incorrect | Sprint 4 | Frontend Dev | UI | Adjusted layout | Closed | Corrected
17 | November – Week 4 | Tester | Email alert delayed | Sprint 5 | Backend Dev | Performance | Optimized mail service | Closed | Improved
18 | November – Week 4 | Tester | Product image upload error | Sprint 5 | Backend Dev | Functional | Fixed file handling | Closed | Working
19 | November – Week 5 | Tester | Mobile view broken | Sprint 5 | Frontend Dev | UI | Fixed responsiveness | Closed | Responsive
20 | November – Week 5 | Tester | Audit logs missing entries | Sprint 5 | Backend Dev | Functional | Fixed logging logic | Closed | Logged
21 | December – Week 1 | Tester | Bulk upload fails for large file | Sprint 5 | Backend Dev | Performance | Optimized upload | In Progress | Testing
22 | December – Week 1 | Tester | Barcode scan not detected | Sprint 6 | Backend Dev | Functional | Under analysis | Open | Pending
23 | December – Week 2 | Tester | Expiry date validation missing | Sprint 6 | Backend Dev | Functional | Validation planned | Open | Pending
24 | December – Week 2 | Tester | Stock history not displayed | Sprint 6 | Backend Dev | Functional | Fix in progress | In Progress | Ongoing
25 | December – Week 3 | Tester | Dark mode UI inconsistency | Sprint 6 | Frontend Dev | UI | CSS fix planned | Open | Pending
26 | December – Week 3 | Tester | Warehouse data mismatch | Sprint 7 | Backend Dev | Data | Analysis started | Open | Pending
27 | December – Week 4 | Tester | API error not logged | Sprint 7 | Backend Dev | Functional | Logging enhancement | In Progress | Ongoing
28 | December – Week 4 | Tester | Backup not triggering | Sprint 7 | Backend Dev | Functional | Scheduled fix | Open | Pending
29 | December – Week 5 | Tester | Dashboard chart loading slow | Sprint 8 | Frontend Dev | Performance | Optimization planned | Open | Pending
30 | December – Week 5 | Tester | Monthly report incorrect | Sprint 8 | Backend Dev | Data | Fix planned | Open | Pending

## Sheet2
Logical
User Interface
Maintainability
Standards
Others