## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As an admin, I want to add new products so that inventory is maintained | Must | None | Backend Developer | Completed
Sprint 1 | Sprint 1 | US-02 | As an admin, I want to update product quantity | Must | US-01 | Backend Developer | Completed
Sprint 1 | Sprint 1 | US-03 | As a user, I want to view inventory list | Should | US-01 | Frontend Developer | Completed
Sprint 1 | Sprint 1 | US-04 | As an admin, I want to edit product details | Must | US-01 | Backend Developer | Completed
Sprint 1 | Sprint 1 | US-05 | As an admin, I want to delete products | Should | US-01 | Backend Developer | Completed
Sprint 2 | Sprint 2 | US-06 | As an admin, I want low stock alerts | Could | US-02 | Backend Developer | Completed
Sprint 2 | Sprint 2 | US-07 | As an admin, I want to search products by name | Should | US-03 | Frontend Developer | Completed
Sprint 2 | Sprint 2 | US-08 | As an admin, I want to filter products by category | Should | US-03 | Frontend Developer | Completed
Sprint 2 | Sprint 2 | US-09 | As an admin, I want product validation before saving | Must | US-01 | Backend Developer | Completed
Sprint 2 | Sprint 2 | US-10 | As a user, I want pagination in inventory list | Could | US-03 | Frontend Developer | Completed
Sprint 3 | Sprint 3 | US-11 | As an admin, I want user login authentication | Must | None | Backend Developer | Completed
Sprint 3 | Sprint 3 | US-12 | As an admin, I want role based access | Must | US-11 | Backend Developer | Completed
Sprint 3 | Sprint 3 | US-13 | As a user, I want logout functionality | Should | US-11 | Frontend Developer | Completed
Sprint 3 | Sprint 3 | US-14 | As an admin, I want to view dashboard summary | Could | US-03 | Frontend Developer | Completed
Sprint 3 | Sprint 3 | US-15 | As an admin, I want session timeout | Could | US-11 | Backend Developer | Completed
Sprint 4 | Sprint 4 | US-16 | As an admin, I want supplier details management | Should | None | Backend Developer | Completed
Sprint 4 | Sprint 4 | US-17 | As an admin, I want to assign supplier to product | Should | US-16 | Backend Developer | Completed
Sprint 4 | Sprint 4 | US-18 | As an admin, I want purchase history tracking | Could | US-02 | Backend Developer | Completed
Sprint 4 | Sprint 4 | US-19 | As an admin, I want export inventory report | Could | US-03 | Backend Developer | Completed
Sprint 4 | Sprint 4 | US-20 | As a user, I want print inventory report | Could | US-19 | Frontend Developer | Completed
Sprint 5 | Sprint 5 | US-21 | As an admin, I want email notification for low stock | Could | US-06 | Backend Developer | In Progress
Sprint 5 | Sprint 5 | US-22 | As an admin, I want product image upload | Should | US-01 | Backend Developer | Completed
Sprint 5 | Sprint 5 | US-23 | As a user, I want responsive UI | Should | US-03 | Frontend Developer | Completed
Sprint 5 | Sprint 5 | US-24 | As an admin, I want audit logs | Could | US-12 | Backend Developer | In Progress
Sprint 5 | Sprint 5 | US-25 | As an admin, I want bulk product upload | Could | US-01 | Backend Developer | In Progress
Sprint 6 | Sprint 6 | US-26 | As an admin, I want barcode support | Could | US-01 | Backend Developer | Planned
Sprint 6 | Sprint 6 | US-27 | As an admin, I want product expiry tracking | Could | US-01 | Backend Developer | Planned
Sprint 6 | Sprint 6 | US-28 | As an admin, I want stock adjustment history | Should | US-02 | Backend Developer | Planned
Sprint 6 | Sprint 6 | US-29 | As a user, I want dark mode UI | Could | US-03 | Frontend Developer | Planned
Sprint 6 | Sprint 6 | US-30 | As an admin, I want system performance optimization | Could | US-01 | Backend Developer | Planned
Sprint 7 | Sprint 7 | US-31 | As an admin, I want multi-warehouse support | Could | US-01 | Backend Developer | Planned
Sprint 7 | Sprint 7 | US-32 | As an admin, I want warehouse stock view | Could | US-31 | Frontend Developer | Planned
Sprint 7 | Sprint 7 | US-33 | As an admin, I want product status active/inactive | Should | US-01 | Backend Developer | Planned
Sprint 7 | Sprint 7 | US-34 | As an admin, I want API error logging | Should | US-01 | Backend Developer | Planned
Sprint 7 | Sprint 7 | US-35 | As an admin, I want backup and recovery | Could | None | Backend Developer | Planned
Sprint 8 | Sprint 8 | US-36 | As an admin, I want dashboard charts | Could | US-14 | Frontend Developer | Planned
Sprint 8 | Sprint 8 | US-37 | As an admin, I want monthly stock report | Could | US-19 | Backend Developer | Planned
Sprint 8 | Sprint 8 | US-38 | As a user, I want faster page loading | Should | US-10 | Frontend Developer | Planned
Sprint 8 | Sprint 8 | US-39 | As an admin, I want configurable stock limits | Could | US-06 | Backend Developer | Planned
Sprint 8 | Sprint 8 | US-40 | As an admin, I want system documentation | Could | None | Backend Developer | Planned
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7